UNITED NATIONS CHILDREN'S FUND

TERMS OF REFERENCE FOR IMPACT EVALUATION OF VOLUNTEER COMMUNITY MOBILIZERS NETWORK ON POLIO ERADICATION IN NIGERIA

INSTITUTIONAL CONSULTANCY

UNICEF NIGERIA

- Background

UNICEF supports communication/social mobilization component of polio eradication programme through an established Volunteer Community Mobilizers (VCM) network to enhance acceptance and create demand for childhood vaccination services, with focus on polio high risk states in Northern Nigeria.    With the passage of time, nutrition, child protection and emergency coordination were included as integrated services, in addition to Polio Eradication Programme.  As a result of the joint and integrated efforts with partners, tremendous progress has been made in the country towards polio eradication.  No case of Wild Polio Virus (WPV) has been reported in the country for the past more than 2 and half year.

Historically, Northern States of Nigeria have mainly been contributing to the Burdon of polio cases due to a variety of reasons.  A reasonable number of children was missing during the Immunization plus Days (IPDs), mainly due to the issues of trust, acceptance and misconceptions about the vaccine.  The 23rd Expert Review Committee (ERC) in March, 2012 emphasized the need to rapidly improve campaign quality in the worst performing Local Government Areas (LGAs).  The committee also recommended to expand and intensify efforts to identify and resolve non-compliance, coupled with understanding and addressing social reasons for missing children.  President of Nigeria declared polio eradication as a national emergency in April, 2012, with increased national funding for the programme and Nigeria National Polio Eradication Emergency Plan was developed.

UNICEF has a strong history of working in the area of social mobilization and used this as a basis for addressing the issue of missed children.  Building upon the piloted results oriented community-based communication initiatives in three selected northern States in 2012, UNICEF initiated Volunteer Community Mobilizers (VCM) network.

The purpose of establishing VCM network was to maximize the outcomes of communication efforts by working with the resistant communities., contribute to reduction in the number of children who are missed during IPDs by using targeted house-to-house interventions to generate demand for and acceptance of the oral polio vaccine.  VCMs are predominantly female hired from the local settlements who are trained to work as “change agents” in their communities.  A VCM must have criteria such as; resident of the same settlement assigned to her, selected through a consultative process with community, preferably educated, elderly (mature) and well respected within the settlement; can fill various coloumns of her register appropriately or has someone to do it for her; can conduct House to House (H2H) and do Inter Personal Communication (IPC); supports pre, during and post-IPDs implementation activities and; has a mobile phone or has access to one through a close relative.

VCMs conduct micro census in beginning of the year and register target groups (pregnant women, under one-year children and under 5 years children) in different parts of their registers.  Subsequently, they refer pregnant women and under one year children to avail Antenatal Care (ANC) and immunization services, respectively, vices at the health facilities, They hold community awareness meetings and organize community dialogues in their settlements, inform community about dates of Supplemental Immunization Activities (SIAs), accompanying house-to-house vaccination teams during IPDs to facilitate identifying houses with children < 5 years of age and ensure their vaccination, tally vaccination coverage and track reasons for missed children in the register meant for the purpose.  On the average, each VCM is responsible for 170-200 households in selected high-risk settlements, identified by using the available data and prioritized within the high risk states of Northern Nigeria.  VCMs work in their own community to track child births and are responsible for resolving non-compliance to vaccination and tracking unimmunized children. VCMs carrying out door-to-door communication interventions with caregivers on issues related to immunization and other key household practices. In hard-to-reach settlements, VCMs provide a crucial link between communities and health care services.

Since 2012, the network has grown and established a strong base of trained and skillful resources of more than 1,300 female and local VCMs operating in high risk settlements of the high risk states.  A comprehensive supervisory and mentorship structure is available at cluster, LGA and ward level to support the VCMs to efficiently perform in their assigned areas. A variety of data recording and reporting tools are in use and different reports related to VCM network are produced with different frequencies. In 2018, more than 55 million children were reached with polio vaccine during the National Immunization Plus Days (NIPDs). Refusal of the vaccine has been reduced to less than 1% due to the success of the trust built by the VCM network and their social mobilization partners.

Keeping in view the evolving and dynamic nature of the programmme over the years, the VCM network focus has been expanded beyond polio to the areas including Antenatal Care (ANC), Routine Immunization (RI) and other integrated areas of social mobilization.  Over the years, the network has produced desired results. Knowledge, awareness, behavior and practices related to OPV and community trust on OPV is at a reasonable level. The number of missed children and more specifically non-compliance have been reduced considerably.  In the past 4 years the network has contributed a lot, awareness and trust about OPV has increased, number of overall missed children and especially noncompliance during the IPDs has reduced   and finally the country has quite closer to achieve the goal of polio eradication.  The last reported polio cases during 2016, were from the inaccessible areas of Borno state where there was no VCM structure available.  Since inception, no proper evaluation of the network has been conducted, so far.  In the current scenario, work of VCMs is evolving.  Therefore, there is a need to conduct a proper evaluation of VCMs.    The following table shows summary of members of VCM network.

| STATE | Total number of VCMs | PSG | Total VCMs + PSGs | Total VWS | LGA Polio Facilitator | State Facilitator |
| --- | --- | --- | --- | --- | --- | --- |
| Bauchi | 450 | 86 | 536 | 45 | 15 | 2 |
| Borno | 2,076 | 41 | 2,117 | 204 | 13 | 5 |
| Jigawa | 1,036 | 83 | 1,119 | 105 | 17 | 1 |
| Kaduna | 1,578 | 240 | 1,818 | 159 | 29 | 4 |
| Kano | 3,808 | 423 | 4,231 | 374 | 52 | 7 |
| Katsina | 2,280 | 97 | 2,377 | 227 | 33 | 8 |
| Kebbi | 300 | 73 | 373 | 30 | 7 | 1 |
| Niger | 950 | 0 | 950 | 95 | 12 | 3 |
| Sokoto | 876 | 217 | 1,093 | 90 | 18 | 3 |
| Taraba | 350 | 0 | 350 | 35 | 8 | 3 |
| Yobe | 1,188 | 0 | 1,188 | 118 | 12 | 1 |
| Zamfara | 740 | 125 | 865 | 66 | 14 | 1 |
| Total | 15,632 | 1,385 | 17,017 | 1,548 | 230 | 39 |

PSG		Polio Survivor Group

VWS	Volunteer Ward Supervisor

Theory of Change

The Polio programmme through the activities of the VCMs during 2018, has tracked more than 540,000 newborns and 73% (392,900) of them were vaccinated with polio vaccine newborns monthly. During 2018, the VCMs conducted 12.7 Million visits to households and sensitized 17.1 million caregivers.  Members of VCM network reached to 4.6 Million caregivers through 304,000 compound meetings and sensitized them on polio vaccination, Routine Immunization, Sanitation, Hygiene and Exclusive Breast-feeding. Another 554,000 People participated in 38,000 community dialogues organized by VCMs.  During the same period, VCM reported 980 Suspected AFP cases of Acute Flaccid Paralysis (AFP), as part of strengthening of community based surveillance and 288 of those cases were assign and EPID Numbers.

The VCM have faced challenges of: Insecurity - making community engagement a challenge; Low risk perception, especially among the political leadership; Waning support of Governors and LGA Chairmen for counterpart funds and oversight roles and; Demands of community for other felt needs affecting acceptance of polio vaccination

- Purpose and Objectives

The purpose of this evaluation is to generate evidence and systematically/scientifically document the contributions of the network towards polio eradication so far (effectiveness, efficiency and impact), review its capacity (relevance), and working mechanism in coordination with other programmme (sustainability).   It is also to determine the extent to which UNICEF supporting activities were effective and inform about planning and implementation of the future community based interventions.

This evaluation is commissioned for the purpose of Learning and Accountability about What Worked very well and what didn’t work and Why vis-a-vis the Theory of Changes and expected results of VCM. Regarding Learning, this independent evaluation will generate sound evidence on driving factors of success or shortfalls of this Community Based interventions for polio eradication that will inform the Ministry of Health’s scaling up strategy of Community based Workers for strengthening the MNCHA/ PHC system.

Regarding Accountability, this independent evaluation will enable UNICEF to provide to Government, States and Donors objective assessment of the Merit and Value for Money of the VCM programme following 5 years implementation of this large investments and capacity development.

Evaluation Users:

| Evaluation Users | Uses |
| --- | --- |
| Federal Ministry of Health | To use the findings in initiating/scaling up of similar community-based interventions/programmes. |
| Departments and Agencies | To use the findings in initiating/scaling up of similar community-based interventions/programmes. |
| Other line Ministries | Use the findings while initiating similar community-based interventions. |
| State Ministries of Health | To use the lessons learnt to strengthen the existing similar community-based interventions/programmes. |
| UNICEF & Development Partners | Use recommendation of the evaluations for community based initiatives to be introduced in future. |
| CSOs/NGOs | Use recommendation of the evaluations for community based initiatives to be introduced in future. |
| Private Sector |  |

The specific objectives of the evaluation are as follows:

- Determine the impact and contribution of the volunteer community mobilizers network towards reducing social barriers to health services and of interest in achieving the target of polio eradication, specifically in 12 polio high risk Northern states of Nigeria.

- Analyse How the VCM strategies, and UNICEF supporting interventions in combination, have contributed to the observed changes in polio program in Nigeria and assess the VCMs performance in coordination with other PHC programmes/services and suggest improved synchronisation.

- Determine to what extent, VCMs are equipped with the required knowledge/skills needed for an integrated communication/social mobilization package, beyond polio and they have the required material for social mobilization.

- Analyse the unintended outcome of the VCM network and how it has contributed to improved health outcomes of children in communities, in particular the most hard to reach.

- Identify strengths and weaknesses in VCM with a focus on the main programmatic strategies used, partnerships, the use of evidence to improve Program performance and the cross cutting issues of gender and the environment;

- Identify lessons learnt and generate strategic recommendations for future implementation and scaling up of VCMs areas of work and their sustainability within the system.

- Evaluation Scope

The Scope of the evaluation has been structured in 4 aspects for better clarity in respect of global standard

## 3.1. Thematic Scope

The evaluation will cover mostly the health community based interventions related to Polio eradication, implemented through the VCM network and with respect to the Theory of Changes presented above. However, this mechanism has been used also for other sectoral interventions like WASH and Nutrition for which assessment of multi sector benefits will be performed. Information from other evaluations and reviews of the health, Nutrition, surveillance, emergencies, protection, Polio programs that were conducted within the UNICEF country program of cooperation of 2009 - 2013 as baseline, will be used. Where possible routine baseline information will also be used to measure change.

## 3.2. Geographic Scope

The evaluation will focus only on 4 States among the 12 of Northern Nigeria in which the programme has been in implementation from 2013 and one non VCM state.   The table already mentioned on page2 indicates names of the state where the VCMs are available and evaluation to be conducted. For the Purpose of assessing the impact of VCM network, one State that never benefit of VCM programme will be selected for HH Survey and other data collection (refer to section 6.1 related).

## 3.3. Periodic Scope

Independent Evaluation of VCM will be cover the 6 years period of the development and implementation of the community-based strategy of polio eradication from 2013 to 2018. This long term period will enable sufficient times to assess both the impact and sustainability of the programme and causality analysis of driver factors for in-depth lessons learned.

## 3.4. Evaluability Assessment

The Impact evaluation will include an evaluability assessment that will inform the decision of proceeding with an impact evaluation at this time and inform the evaluation design and focus. According to OECD DAC, an evaluability assessment is: “The extent to which an activity or project can be evaluated in a reliable and credible fashion”.

The purpose of the Evaluability Assessment is thus threefold:

- To ensure that the embedded Theory of Change (ToC) of VCM programme is consistent with existing evidences, and is sound;

- To explore the availability of existing performance management system and data as it relates to VCM in Nigeria;

- Finally, to explore conduciveness of the program context as they relate to VCM ensure that stakeholders, are aware and interested in an evaluation of the VCM.

- Design of the VCM program

- Are the VCM program long-term impact and outcomes clearly identified and are the proposed steps towards achieving these are clearly defined and meet standards for Results-Based Management?

- Is the VCM program theory of change available, sound and consistent with the problem to be addressed?

- Is the design of VCM program appropriate and based on sound understanding of local context?

  - Are resources and VCM program designed to effectively respond to local conditions (including risks), capacity gaps and related problems that has been identified?

- Availability of Data

- Is a complete set of documents available with respect of the VCM program, resources, and beneficiaries and activities and related objectives?

- Is data being collected for all the indicators as they relate to the Theory of Change? Is gender disaggregated data available with respect of VCM program?

- Conduciveness of the program context

- Identify their understandings of program purpose, design and implementation, including areas of agreement and disagreement.

- Identify their expectations of an evaluation, it objectives, process and use.

- Clarify and fill in gaps found in document review.

The Evaluability assessment  observations and conclusions, shall inform the evaluation focus by either suggesting additional sub questions or modifying existing one, should the EA recommend to go forward with an evaluation.

- Evaluation Criteria and Questions

## 4.1. Evaluation Criteria

The evaluation criteria against which the programme will be assessed will be the OECD DAC criteria covering Impact, Relevance, Effectiveness, Efficiency and sustainability of the programme. All the elements of this criteria will be in line with the programmes results framework/Log frame indicators from which the evaluation questions will also be drawn.

## 4.2. Evaluation Questions

The impact evaluation will be guided by the following indicative list of evaluation questions. Depending on recommendations of the Evaluability Assessment, the following criteria and corresponding Evaluation questions shall focus the Impact Evaluation study of VCM program as follow:

Impact

- What is the impact of VCM network in reducing social barriers to health services at community level?

- What is the impact of VCM in contributing (making difference) to the reduction of Polio Case in targeted champion state & communities and what are the driving factors?

- What is the impact of the VCM program on the greater equity in VCM resources allocation and increased in budget allocations for child survival services in targeted communities?

- What is the impact of the VCM program on improved health in targeted communities?

- What are the un-intended impact of VCM Network (positive or negative)?

Effectiveness

- To what extent did the Program achieve its expected results, in particular at the output level?

- Are Primary Health Care Services fully functional in delivering Polio Vaccination Services?

- Where the assumptions underlying the programme’s intervention strategy correct?

- To what extent were women involved in VCM at community level?

Efficiency

- Where expected results (outputs) delivered within budget? How does the cost-effectiveness (Value For Money) of different programme components compare across sites (targeted communities)?

- Is the Supply Chain Management Efficient (Cold Chain and Delivery/availability of Vaccines)

- What were the most important cost drivers in the programme and how can costs be contained without compromising results?

- What are unintended outputs resulted from VCM regarding the Theory of Changes?

Relevance

- To what extent are the objectives of the Program valid in relation to overarching plans of the Government of Nigeria (National Health Development Strategic Plan)?

- To what extent did the services of VCM meet the specific needs of children, especially girls, and the most deprived ones in terms of distance?

- To what extent are the objectives and the approach of the VCM Program responsive to the needs, context and priorities of the targeted population?

- Any question about placement/deployment in relevant geographic areas?

Sustainability

- To what extent has the VCM Program contributed to strengthened governance of community structures?

- To what extent has government capacity, including evidence-based communication planning, monitoring and information management for the delivery of community health service strengthened as a result of VCM program?

- Overview Evaluation Frame and Approach

The evaluation will occur in several phases:

Inception phase:

Inception phase, during which an evaluability assessment will be conducted. The main objective of the evaluability assessment is to determine the best evaluation approach and design for the impact evaluation, considering the constraints of time, data availability, budget and methodology.

As a consequence, the approach and methodology to be employed during the data collection phase will be developed by the team and report into an inception report which will include a data analysis plan.  The evaluability assessment findings shall inform the inception. The data analysis plan, will specify which of the proposed procedures related to the data will be utilised and how the data will be analysed in detailed. The data analysis plan is integral part of the inception report which includes the evaluation plan and data analysis plan.

Data collection phase:

The data collection phase, is the implementation of the revised and final approved evaluation plan, as per the inception report. The data collection phase consists of field data collection through several methodology, such as house hold survey, key informant interviews, focus groups, desk review and use of secondary data such as national statistics or administrative data.  Aligned with the approved evaluation plan and design and the major analytic work is completed. This shall include sample size and selection; household survey, focus group discussions, data collection at the community level and related field work, as relevant.

Reporting phase:

The reporting phase is comprise of several steps: data processing and analysis of quantitative HH Survey plus the transcription/synthesis of qualitative information (FGD and Kii) and may subsequent process reports. First, as it will be agreed with project authority, regular ongoing reports (weekly or bi-weekly as agreed) is expected between project authority and contractors.  The content of the report will be light and meant to inform on the ongoing progress of the evaluation implementation phases. Progress towards milestones of the evaluation plan, emerging challenges, and need for support from project authority will be reported regularly.

Towards the end of the evaluation, during which a draft report is delivered, aligned with UNEG (United Nations Evaluation Group) standards, for comments and approval. The final global evaluation report addressing all comments should be submitted within a month to project authority and to the steering committee for approval. It is expected that the Team self-assess the Evaluation report with the GEROS tools and submit the tools along with the draft report.

Quality expectations

It is expected that the evaluation design will deal with the four dimensions of quality of impact evaluation and the proposal will demonstrate how it will successfully address the following:

•	Statistical conclusion validity;

•	Construct validity;

•	External and;

•	Internal validity.

Statistical conclusion validity is concerned with whether the presumed cause of the VCM interventions and the presumed effect (the impacts as per the revised Logic model) are related. Measures of effect size and their associated confidence intervals should be calculated. Statistical significance (the probability of obtaining the observed effect size if the null hypothesis of no relationship were true) should also be calculated.

Construct validity refers to the adequacy of the operational definition and measurement of the theoretical constructs that underlie the VCM outcomes and impact. We need to ensure that we indeed measure what we had intended to change.

External validity refers to the generalizability of causal relationships across different persons, places, times, and operational definitions of interventions, outcomes and impacts.

Finally, the internal validity refers to the correctness of the key question about whether the VCM intervention really did cause a change in the outcome and impact expected. Essentially is the evaluation design appropriate and deal with a counterfactual e.g. what would have happened to the VCM clients (experimental units) if the intervention had not been applied to them?

- Methodological Approach

## Overall Design approach

The Consult Firm will develop adequate Design and methodology of this evaluation within the detailed Inception Report.

However, this impact evaluation will apply the Theory Based Approach in assessing the Theory of Change of VCM and will use evidence from mixed methods of data collection that will meet expectations derived from the Objective and Evaluation Questions.

The proposed approach should also deal with causality by determining the attribution on the outcomes caused by the VCM program (i.e. use of counterfactual).  The Quasi experiment design approach will be used to assess the impact of the programme through the application of the approach of comparing results achieved in LGAs/Communities that benefited of VCM programme (Treatment group) with LGAs/Communities which were not covered by the VCM programme (the control group). Quantitative HH Survey plus FGD will be undertaken in both Treatment group and Control Group. In Addition, administrative routine data and qualitative information will be collected analysed for assessing other criteria and performing causality analysis.

Those two categories of communities will be identified using a statistically relevant sample. The consultants will produce a sampling plan that will include at minimum:

- Power calculations and sample size determination at the community and household level to ensure robust measures of estimated impacts;

- Sampling frame and plans for numeration and listing;

- Cleary define probabilities of selecting the target population;

- Coding strategy;

- Sampling weights to be used in the data analysis;

- The methodology will be further refined and informed by an Evaluability assessment.

The approach and methodology should include, but not limited to, the following:

- A quasi-experimental approach, such as matching methods, regression Discontinuity design or other as relevant (contribution analysis) while meeting the quality criteria.

- Ensure that all data collection processes, analysis and training of field staff, as relevant, are subject to a Quality Assurance plan that will be detailed in the Inception report.

- Incorporate data from the existing monitoring and information system implemented by the partners and other relevant sources of information available as identified during the evaluability assessment;

- As required help direct data collection activities to ensure that the necessary activities, outputs and outcomes are being measured.

- Develop questionnaires for the household and community surveys, as relevant. Both the quantitative and qualitative questionnaires will be pre-tested and revised accordingly. The field procedure plan will be drawn up including the number of enumerators, field supervisors, field data entry agents, training plan and expected tasks and responsibilities. A robust data entry programme will be drawn up.  A CAPI (Computer Assisted Personal Interviewing) approach to household survey, SHOULD a house survey have been proposed, is strongly recommended.

- A data analysis plan, in which the procedures related to the data to be analysed under the evaluation design and sampling plan will be described and detailed. The data analysis plan is integral part of evaluation plan.

- An evaluability assessment, should be undertaken

## Suggested indicators to measure the Evaluation objectives and questions

Following are some of the suggested indicators to be used for parameters of effectiveness, impact, efficiency, relevance and sustainability aligned to the Theory of Changes and VCM Program Results Matrix Framework.  These proxy indicators can further be refined and finalized at the time of questionnaire development and analysis.

Table: Measurement of evidence against Evaluation’s Criteria and Questions

| Criteria | Evaluation Questions | Key Indicators for measurement | Data/Information Sources for credible evidence |
| --- | --- | --- | --- |
| Impact | 1-What is the impact of VCM network in reducing social barriers to health services at community level? 2-What is the impact of VCM in contributing (making difference) to the reduction of Polio Case in targeted champion state & communities and what are the driving factors? 3-What is the impact of the VCM program on the greater equity in VCM resources allocation and increased in budget allocations for child survival services in targeted communities? 4-What is the impact of the VCM program on improved health in targeted communities? 5-What are the un-intended impact of VCM Network (positive or negative)? | Impact & Outcomes Indicators: -Trend of Number of wild Polio cases per State -Reduction in childhood vaccine preventable diseases. - Reduction in number of missed children due to refusals. - Improved family life of VCMs. | -HH Survey – Primary Data Collection in Treatment and Control Group Sample Communities/States. -MICS 2011, MICS 2016-2017; -DHS 2018; -Routine Administrative Statistical Data from MoH – EPI (NIHS) -FGD/KII – WHO Independent Monitoring data- AFP surveillance data. |
| Effecti-veness | -To what extent did the Program achieve its expected results, in particular at the output level? -Are Primary Health Care Services fully functional in delivering Vaccination Services? -Where the assumptions underlying the programme’s intervention strategy correct? -To what extent were women involved in VCM at community level? | Outputs Indicators: - Children received polio vaccine in all polio campaigns. -Caregivers aware about the dates/days of recent IPDs and have knowledge of polio disease and other vaccine preventable diseases. - Missed children/ refusals during rounds of IPDs. - PHC having functional routine immunization centres. - Detailed reasons for Missed Children. -Pregnant women who visited health facilities for Antenatal Care services. |  |
| Efficiency | -Were expected results (outputs) delivered within budget? How does the cost-effectiveness (Value For Money) of different programme components compare across sites (targeted communities)? -Is the Supply Chain Management Efficient (Cold Chain and Delivery/availability of Vaccines) -What were the most important cost drivers in the programme and how can costs be contained without compromising results? -What are unintended outputs resulted from VCM regarding the Theory of Changes? | Value For Money indicators: - Unit Cost of VCM. - Availability of visibility, health education and social mobilization material, recording/ reporting and monitoring/supervisory tools at different levels. - PHC having Staff and cold chain equipment. - Community having operational VCM? | -MOH Health Facility Assessment; -Communication updates – WHO LQAs results of polio campaigns – Independent Monitoring data after polio campaigns. |
| Relevance | -To what extent are the objectives of the Program valid in relation to overarching plans of the Government of Nigeria (National Health Development Strategic Plan)? -To what extent did the services of VCM meet the specific needs of children, especially girls, and the most deprived ones in terms of distance? -To what extent are the objectives and the approach of the VCM Program responsive to the needs, context and priorities of the targeted population? -To what extent VCMs have been placed/deployed in relevant geographic areas, based on high risk criteria? | - Reduction in number of polio cases. -Children received childhood vaccination for vaccine preventable diseases, beyond polio. -Number of polio vaccination refusals in VCM assigned areas. -Increase in level of awareness and knowledge of caregivers about childhood vaccination. - Proportion of VCMs placed in the settlements identified through the high risk criteria. | Plans, polices and frameworks |
| Sustai-nability | -To what extent has the VCM Program contributed to strengthened governance of community structures? -To what extent has government capacity, including evidence-based communication planning, monitoring and information management for the delivery of community health service strengthened as a result of VCM program? | - % wards with functional Ward Development Committees (WDCs). -% LGAs developing evidence based monthly/campaign specific communication plans. |  |

Contribution of VCM network towards polio eradication programme (effectiveness, efficiency and impact)

- Overall missed children, with special focus on non-compliance since inception of the network, so far.

- Caregiver’s knowledge about transmission and symptoms of polio and Oral Polio Vaccine.

- Caregiver’s knowledge about RI, childhood vaccine preventable diseases and RI schedule.

Capacity of VCMs (relevance)

- VCMs and their supervisors who have received training in the past two years.

- VCMs having complete communication package of required IEC material for use during social mobilization activities and recording tools to maintain record of the target groups in their assigned areas.

Coordinated working mechanism with other integrated services such as in Nutrition, Child protection, emergencies, Sustainability).

- VCMs and  their supervisors working in close coordination with other programmes ( such as Hard to reach mobile teams, ANC/RI, birth registration etc.)

## Major Tasks to be accomplished

The tasks to be completed by the contractor include, but are not necessarily limited to the following:

- Review background documentation on the VCM program intervention, other VCM intervention and evaluations in Nigeria or abroad, as well as all relevant information.

- Perform a literature review on VCM program interventions (evaluation and research), and ensure that it feed the impact evaluation approach and design.

- Validate the Theory of Change (Logic model) as required, using both documentation and participatory interview or focus group sources of data.

- Meet with relevant stakeholders, such as donors, private sector, government partners  directed by UNICEF.

- Present for, approval by UNICEF, an inception report containing the evaluability assessment findings, a detailed Evaluation Plan, data analytical plan and evaluation design that address the specific evaluation questions and quality expectations.

- Propose potential evaluation questions that will allow us to meet the evaluation objectives, relevant indicators, data collection methods and present evaluation design options to meet the quality expectation state herein.

- Identify relevant control group or relevant strategy (such as Theory based, INUS and contribution analysis) to identify a counterfactual, for attribution or contribution analysis as part of the evaluation design; and suggest new evaluation questions to reflect the proposed changes.

- Propose relevant data collection strategy, sample size, and household survey for impact analysis.

- Implement the Approved Evaluation Work Plan as per the approved inception report.

- Liaise with the Stakeholders through email, teleconference, in-person meetings as needed.

- Inform proactively the project authority (UNICEF Nigeria) of any significant modifications to the intervention/project that could affect the evaluation and any difficulties that may arise in implementing the approved evaluation design.

- Prepare the inception and the draft evaluation report described as the agreed deliverables table.

- Prepare and PowerPoint presentation and disseminate the evaluation;

- Undertake any reasonable task associated with the evaluation within the period of engagement.

## Existing information sources:

Identify relevant information sources that exist and are available, such as:

- Pre-intervention or baseline reports

- UNICEF VCM Programme Results framework (RAM Planning and reporting)

- Project documents and reports for the period 2013-17

- Past related HH surveys, studies, evaluations for the period of 2013-17

- Data from government offices/sources

- Plans, polices and frameworks

- Existing dashboard (BR tracking) and campaign data from February 2015 to date.

- End Product: (e.g. final report, article, document etc.)

- An Evaluability Assessment report.

- An inception report, detailing the (i) evaluation design, (ii) detailed work plan (iii) cost and detailed (iv) data analytical plan.

- Periodic updates (weekly or bi-weekly as needed) and a final Evaluation Report, which should include

  - Executive summary

  - Methodology:  description of sampling and evaluation methodology used, assessment of methodology and its limitation, data collection instruments, and data processing (analysis methodology, and quality assurance)

  - Findings;

  - Conclusions;

  - Recommendations (if any);

  - Lessons learned;

  - Annexes:  List of indictors, questionnaires, and if survey, table of sample size and sample site as appropriate

- The Final reports should be provided in both hard copy and electronic version in English in the required UNICEF format (UNEG standards), respecting UNICEF Style Book (2014).

- Completed data sets (filled out questionnaires, records of individual interviews and focus group discussion, etc.)

The Final evaluation report will be required to follow “UNICEF Evaluation Report Standards” and UNICEF Evaluation Technical Notes and be aligned with UNEG Standards and Norms.  A self-assessment of the draft report against the GEROS Unicef tool will also be required.

- Evaluation Governance & Stakeholder participation & Quality Assurance

The evaluation will be steered by a Steering Committee co-chaired by UNICEF and National Primary Health Care Development Agency (NPHCDA) and composed of the Federal Ministry xxxxxxxxxx, Federal Ministry of xxxxxxxxxxx),   FOMWAN, State Ministry of Health (SMoH), National Orientation Agency, National/State Primary Care Health Development Agency,) and polio partners (WHO, Core Group of Polio Partners, Bill and Melinda Gates Foundation UNICEF and respective cooperating partners.  The Steering committee will be supported by the evaluation team who will also serve as secretariat.  The TORs of the committee include the following responsibilities:

- Review and recommend for approval of the all deliverables of the evaluation, including evaluability, inception report, evaluation final reports as well as the evaluation plan.

- During the inception phase review the proposal by the service provider and recommend changes as appropriate.

- Review the inception report, recommend changes if needed, and recommend for approval the inception report.

- Review and recommend for approval the data collection instruments and tools where applicable.

- Provide feedback on draft reports, including comments from peer reviewers to the service provider, and a workshop with stakeholders if appropriate.

- Approval of the final report as a satisfactory evaluation report that fulfills the agreed inception report.

- Recommend approval or not of specific recommendations emerging from the report.

- Communicate the results of the approved evaluations.

- Develop minutes of the meeting including all relevant decisions.

- Accountabilities:

The Chief of Evaluation will serve as the primary contact with the evaluation team, will support coordination of the evaluation, by facilitating the evaluation steering committee and provide necessary assistance, information to effectively support the research process. The Chief of communication for Development (C4D) and Monitoring Specialist of polio/C4D will also provide technical support where necessary.

Field Offices

UNICEF field offices will be supporting the evaluation team in conducting related evaluation activities and identifying sources of data as need be and contacts and interviews.

The Regional Office

M&E team will also take advantage of the quality assurance provided by the LTA which shall be in place and available at the Regional level.

Responsibilities related to this consultancy will be divided as follows:

Evaluation Team Leader

- Oversight and management of team members

- Orientation and training of team members, data collection assistants where applicable

- Responsible for meeting deadlines and quality of evaluation products

- Principal authorship of final report

Country Office

- Liaison with the evaluation team

- Collection of relevant internal materials

- Facilitation of new data collection--e.g. set up intranet questionnaires; admin support to trips

- Coordination of stakeholders

- Securing agreement of country and regional offices for field visits

- Review and acceptance of intermediate and final products

- Authorizing payment

Procedures and logistics:

The consultants or firm will be responsible for arranging their own transport, accommodation and other logistics.  The consultant will also be responsible to arrange for two Steering committee meetings, logistic and transport of members.

Risks and Risk Mitigation

It is impossible to predict all the problems and risks that might arise. Those that are considered most likely to appear are the following.

  - Perceptions that the evaluation is threatening the support provided both financially and technically.

Having a steering committee that manage the evaluation and own the findings; An effort will be made from the beginning to communicate the evaluation’s objectives, purpose and scope, and to highlight the need to improve and scale up.

  - Timing presents a major risk for this evaluation.  Time for data collection will be tight.

Country office including Field offices support will be necessary to ensure that time spent in country is well used and documentation sharing happens well before arrival, so that consultants can quickly begin with data collection and logistical issues resolved prior to arrival. In addition, bidders are encouraged to be forthright about whether they recommend a longer period, or the compromises they project emerging if that duration is maintained.

  - Data availability, quality and consistency are to a degree unknown. The mitigation factors will be to perform an evaluability assessment to feed the choice of approaches and methods. It is also expected that the creativity and skill of the consultants in identifying appropriate data source.

- Ethical Considerations:

The Evaluation will follow UNICEF guidelines on the ethical participation of children. In addition, all participants in the study will be fully informed about the nature and purpose of the evaluation and their requested involvement. Only participants who have given their written or verbal consent (documented) will be included in the evaluation. Specific mechanisms for feeding back results of the evaluation to stakeholders will be included in the elaborated methodology. All the documents, including data collection, entry and analysis tools, and all the data developed or collected for this study/consultancy are the intellectual property of UNICEF (may need to add partners names here, including government, as appropriate.) The Evaluation team members may not publish or disseminate the Evaluation Report, data collection tools, collected data or any other documents produced from this consultancy without the express permission of, and acknowledgement of UNICEF (may need to add partners’ names here, including government).

- Dissemination:

Findings of the evaluation will be published to relevant stakeholders as well as through the following

- Validation meetings

- Final Inception and Evaluability reports

- Final evaluation report

- Published on UNICEF global evaluation database.

- UNICEF Nigeria website

- Other knowledge management and sharing platforms.

- Qualifications or specialized knowledge/experience required

The selected firm/consultant must possess the following qualifications:

- Demonstrated experience is sound impact evaluation design

- Excellent report writing and analytical skills

- Previous experience in carrying out impact evaluations for similar programmes;

- Strong capacity and experience in planning and organizing evaluation logistics;

- Strong capacity in data management and statistics.

- Strong background in microeconomics, statistics and econometrics.

- Excellent track record in partnering with African survey firm(s) to conduct the field work.

- Excellent track record of working with Sub-Saharan African clients, including Governments.

- Experience of working in Nigeria an asset.

- Familiarity with UNICEF’s mission and mandate an asset.

- Prior experience in working with multilateral agencies an asset.

- Knowledge of UN role, UN reform process and UN programming at the country level, particularly UNDAF and familiarity and knowledge in the five UNDAF Programming Principles:

- Resource requirements

## 13.1. Budget Costing

Estimate the cost and prepare a detailed budget. Link the budget to the key activities or phases in the work plan. Cost estimates may cover items including:

- Travel: international and in-country

- Team member cost: salaries, per diem, and expenses

- Payments for translators, meeting logistics, interviewers, data processors, and secretarial services.

- Training cost and printing of material if relevant

- Staff (before, during, after)

- Other stakeholders, including primary stakeholders.

## 13.2. Workplan - Estimated time of consultancy and deadline for submission of end product

S. No.; Description of activities; Expected Duration. Preparation phase; July - December 2019. Development of Terms of Reference; 1 week. Constituting the Steering Group; 2 weeks. Identification/Selection of research agency; 10 weeks. Inception phase; Jan - Feb 2020. Inception mission and evaluability assessment; 4 weeks. Inception report the results of evaluability assessment and proposed approaches and methods; 2 weeks. Review of the study plan, protocol, analytical framework and indicators by steering committee; 1 week. Feedback and revision; acceptance of the inception report; 1 week. Data collection phase - Data analysis; March - April 2020. Data collection phase: preparation (conception of household survey, pilot the survey, training of enumerators, etc.) and execution. In the field.; 6-7 weeks. Reporting phase; May - June 2020. Preparation and submission of draft report; 4 weeks. UNICEF feedback on draft report; 2 weeks. Preparation and submission of final report; 1 week. Dissemination of report; 1 week.

- Official Travel and Logistics involved

This consultancy will include travels within Nigeria especially during field work. The will be responsible for arranging its own transport, accommodation, cost of meetings and other logistics for the conduct of the evaluation.  There should be at least 2 steering committee meeting, for which the evaluation team will prepare and organize and act as the secretariat.  One at the inception phase, another at the draft final report.

Comments and Recommendations:

The consultant will report to the chief of evaluation and provide advice on its technical recommendations.

All materials developed will remain the copyright of UNICEF and that UNICEF will be free to adapt and modify it in the future

- Criteria for technical review of proposals submitted by institutional consult firm

Proposals submitted by bidders will be evaluated/rated according to the criteria described in the following tables. The criteria address the following key areas:

- Capacity/capability of the consult firm

The consult firm should demonstrate its previous experience of evaluation and submit at least 2 reports of the latest evaluation it has conducted.  The firm should share its complete profile showing the strengths.

- Qualification and experience of evaluation team members

The proposal should provide a comprehensive description of the research team lead (CV) and the team members proposed to undertake the evaluation (mentioning names, positions, roles and responsibilities in the research). It is expected that the proposed team will comprise of national/international members, responsible for the design, management, analysis, and reporting of the evaluation.  Other/Junior national members will assist in other areas of research and/or field work. National members are encouraged to develop the country capacity; subject to maintain standards of quality in the work.

- Proposed approach and methodology for the research (VCM Evaluation)

The Bidders must describe their understanding of the purpose, scope and context of the evaluation and the methods (including evaluation design) they propose to be used for the evaluation. This section of the proposal must include sufficient detail to enable the Technical Review Committee to apply the criteria for scoring.

Evaluation Sheet

| Description of Criteria | Maximum points | Scoring (Points awarded) | Comments |
| --- | --- | --- | --- |
| - Capability of the consult firm to conduct this research. - Geographic presence of the firm- international presence. - Experience in the area of research. - Previous evaluations conducted for UNICEF | Capable /Not capable |  |  |
| - Qualification and experience of evaluation team members. The bidder should demonstrate: - Details of qualification and experience of research team lead and suitability. - Details of all proposed key team members by name Experience in the area of research (updated CVs). - The proposed resource has experience in designing methodologically rigorous evaluation projects. - A maximum of two recent evaluation reports will be rated on the basis of (I) Design, (II) evaluation instruments (iii) data collection procedures, (iv) data analysis techniques and (v) description of study limitations. (consider a Research methodology, standardized instruments no empirical instruments are use. | 8 6 6 10 (5 points per evaluation report) |  |  |
| Subtotal Marks | 30 |  |  |
| - Proposed approach and methodology for the research (VCM Evaluation). The bidder should demonstrate: - Methodology should demonstrate that it has taken into consideration the evaluation literature on VCM and other related interventions. - Proposed methodology, sampling technique, sample size determination and clearly defined probabilities of selecting the target population. - Explicitly mention threats to validity and describe how to mitigate/address. - Feasibility of evaluation approach/ methodology, taking into account the potential challenges that may arise, risk and how to mitigate them. (Scores may be given on number of challenges and solutions identified) | 6 12 12 10 |  |  |
| Sub Total Marks | 40 |  |  |
| Total Technical Evaluation | 70 |  |  |
| Total Financial Evaluation: Costing/Price | 30 |  |  |
| Grand Total Marks | 100 |  |  |

Signatories

Elaborated by:	   					Reviewed & Certified by:

Last case of Wild Polio Virus, a 2 years old girl, was reported from Monguno LGA of Borno state, with date of onset of 21st August 2016.

Two states with higher and 2 with lower number of VCMs.  Kano and Katsina with higher number of VCMs and Kebbi and Bauchi with less number of VCMs.  Non VCM state will be decided at the time of evaluability assessment

The contractors should be further guided by the following guidance on Evaluability Assessment: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/248656/wp40-planning-eval-assessments.pdf

You might want to refer to this document: Davis, R. (2013) Planning evaluability assessments: A synthesis of the literature with recommendations. DFID Working Paper 40, U.K.